## Project Summary
Address Redacted · RENOVATION PROJECT BUDGET
Pasadena, TX ¦ Active Renovation ¦ Budget as of 2025
DEAL SUMMARY
Metric | Value |  | Metric | Value
Purchase Price | 75200 |  | ARV (Low Estimate) | 215000
Net Acquisition Cost | 81125 |  | ARV (High Estimate) | 230000
Pre-Reno Appraised Value | 160000 |  | Projected Profit (Low) | 71852.3367
Total Renovation Budget | 62022.6633 |  | Projected Profit (High) | 86852.3367
TOTAL ALL-IN COST | 143147.6633 |  | Return on Cost (Low) | 50.19%
Instant Equity (Pre-Reno) | 16852.3367 |  | Return on Cost (High) | 60.67%
Color Key: Blue text = Hardcoded input ¦ Black = Formula ¦ Green = Cross-sheet link ¦ PERT = (Opt + 4×ML + Pess) ÷ 6 hrs × $25/hr
HOUSE ACQUISITION
Description | Amount | — | — | Total | Notes / Assumptions | Reference
Property Purchase Price | 75200 | — | — | 75200 | Agreed sale price | Purchase Agreement
Loan / Mortgage Amount | 71440 | — | — | 71440 | Financed portion (informational) | Lender / Loan Docs
Down Payment (Cash Equity) | 9685 | — | — | 9685 | Purchase price minus loan | Calculated
Total w/ All Closing Fees | 83375 | — | — | 83375 | Includes title, escrow & all fees | Settlement Statement
Seller Contribution | 2250 | — | — | 2250 | Seller-paid closing cost credit | Settlement Statement
NET ACQUISITION COST |  | — | — | 81125 | Total closing cost minus seller contribution | Calculated
CONTRACTOR BIDS (Material & Labor Included in Bid Price)
Description | Material Cost | Labor Hours | Labor Cost | Total Cost | Notes / Assumptions | Source / Detail
Foundation + Flatwork (Driveway & Sidewalk) | Bundled | Bundled | 10627 | 10627 | Incl. $2,000 discount; Driveway, Sidewalk, Interior metal beam under BR2 | Contractor Bid
New Roof (incl. Tear-Off) | Bundled | Bundled | 8267.25 | 8267.25 | Incl. $1,200 discount; full tear-off & replace | Contractor Bid
Electrical Panel Upgrade (100A → 200A) | Bundled | Bundled | 4300 | 4300 | Service upgrade; incl. panel + breakers + permit + labor | Contractor Bid
CONTRACTOR SUBTOTAL |  |  |  | 23194.25
SELF-MANAGED WORK (Material + Labor @ $25/hr)
Category | Material Cost | Labor Hours | Labor Cost | Total Cost | Includes | Source
Exterior Envelope | 5654.6 | 229.3333 | 5733.3333 | 11387.9333 | Siding, sheathing, eave, insulation, windows/door, wall framing, gutters, covered deck, shed removal | PERT + LID sheets
Exterior Finishes | 1624.4 | 67.3333 | 1683.3333 | 3307.7333 | Exterior paint, fence (full perimeter) | PERT + LID sheets
Interior Systems | 7313.9 | 127.8333 | 3195.8333 | 10509.7333 | HVAC, electrical rough-in, water heater | PERT + LID sheets
Interior Finishes | 4064.68 | 142.3333 | 3558.3333 | 7623.0133 | Doors, interior paint, laundry, garage drywall, 1/2 bath, full bath | PERT + LID sheets
Outdoor Structures | 0 | 0 | 0 | 0 | Included in Exterior Envelope | PERT + LID sheets
Misc / Contingency | 6000 | 0 | 0 | 6000 | Buffer for extras not captured elsewhere | Hardcoded estimate
SELF-MANAGED SUBTOTAL | 24657.58 | 566.8333 | 14170.8333 | 38828.4133
| Total Labor Hrs | Total Labor Cost | Total Project Cost
★ TOTAL PROJECT COST | 566.8333 | 14170.8333 | 143147.6633

## PERT Labor Estimates
PERT LABOR COST ESTIMATES
LABOR RATE ($/hr): |  |  | 25
Trade / Item | Fixed Hrs (override) | Opt (hrs) | Most Likely (hrs) | Pess (hrs) | PERT Hours | Labor Cost (@ $25/hr) | Assumptions / Notes
— EXTERIOR WORK —
Siding / Trim | — | 20 | 27 | 35 | 27.1667 | 679.1667 | Fixed 55 hrs — siding panels, trim install (140-hr pkg)
Sheathing + WP | — | 20 | 30 | 40 | 30 | 750 | Fixed 18 hrs — sheathing + waterproof membrane (140-hr pkg)
Eave | — | 20 | 25 | 30 | 25 | 625 | Fixed 25 hrs — carpenter, fascia & soffit
Exterior Paint | — | 20 | 36 | 64 | 38 | 950 | Painter crew; pressure wash, prime, 2-coat spray
Insulation | — | 15 | 20 | 30 | 20.8333 | 520.8333 | Fixed 20 hrs — batt/blow-in whole house (140-hr pkg)
Windows / Patio Door | — | 50 | 60 | 75 | 60.8333 | 1520.8333 | Fixed 22 hrs — remove, install, seal, trim (140-hr pkg)
Fix Damaged Studs | — | 5 | 25 | 50 | 25.8333 | 645.8333 | Fixed 25 hrs — stud repair, sistering, blocking (140-hr pkg)
New Fence | — | 16 | 28 | 48 | 29.3333 | 733.3333 | Fence crew; panels, rails, gates, hardware
Gutters | — | 6 | 10 | 16 | 10.3333 | 258.3333 | Gutter crew; hang sections, install outlets, downspouts, grade & test
Covered Deck | — | 12 | 20 | 36 | 21.3333 | 533.3333 | Carpenter; framing, decking, metal roof
Shed Remove | — | 4 | 8 | 12 | 8 | 200 | Demo, load, haul — confirm dumpster
— INTERIOR & RENOVATION —
Water Heater | — | 3 | 6 | 12 | 6.5 | 162.5 | Plumber: connections, drain pan, flush & test
Electrical (Rough-In) | — | 40 | 80 | 120 | 80 | 2000 | Licensed electrician; rough-in wiring & devices
HVAC | — | 24 | 40 | 64 | 41.3333 | 1033.3333 | HVAC tech; refrigerant, ductwork, startup
Doors | — | 6 | 12 | 20 | 12.3333 | 308.3333 | Carpenter; hang, shim, hardware — all 6 doors
Interior Paint | — | 30 | 52 | 88 | 54.3333 | 1358.3333 | Painter; walls/ceiling, trim, doors
Laundry Rebuild | — | 16 | 28 | 48 | 29.3333 | 733.3333 | Framer + plumber; wall framing + plumbing rough-in
Garage Drywall | — | 6 | 10 | 16 | 10.3333 | 258.3333 | Drywall finisher; hang, tape, mud, sand, prime
1/2 Bath | — | 7 | 13 | 21 | 13.3333 | 333.3333 | Tile setter + plumber/electrician; tile, toilet, faucet, mirror, exhaust fan
Full Bath | — | 12 | 22 | 36 | 22.6667 | 566.6667 | Tile setter + plumber + carpenter; tile, shower, vanity, faucet, sink rough-in, exhaust fan
TOTAL ESTIMATED LABOR |  |  |  |  | 566.8333 | 14170.8333

## Line Item Details
1204 DUNSTAN RD · LINE ITEM COST BREAKDOWNS
Material costs by work category ¦ Blue = input ¦ Black = formula ¦ Update quantities to match actual purchases
SIDING (64 linear ft)
Component / Description | Quantity | Unit | Unit Cost | Line Total | Notes
Siding Panels | 16 | ea | 40 | 640 | LP Smartside 4×8 cedar stamped panel
Nails | 1 | box | 48 | 48 | 2-3/8 in. x 0.113 in. 21° Plastic Collated Exterior Galvanized Ring Shank Round Head Framing Nails 1000 per Box
Siding Battens | 28 | ea | 24 | 672 | 16'×4"×4/4 LP Smartside cedar stamped
Subtotal |  |  |  | 1360
SHEATHING + WATERPROOFING
Component / Description | Quantity | Unit | Unit Cost | Line Total | Notes
ForceField Plywood Sheathing | 15 | ea | 27 | 405 | Weather-resistant sheathing; existing partially retained
Nails | 1 | box | 48 | 48 | 2-3/8 in. x 0.113 in. 21° Plastic Collated Exterior Galvanized Ring Shank Round Head Framing Nails 1000 per Box
ForceField Sheathing Seam Tape | 3 | roll | 20 | 60 | Seam sealing at panel joints
Subtotal |  |  |  | 513
EAVE (fascia & soffit)
Component / Description | Quantity | Unit | Unit Cost | Line Total | Notes
Plywood for Soffit | 1 | ea | 35 | 35 | This is for fixing a few sections of soffit - 3/8 sanded pine plywood
Fascia - Corner | 1 | ea | 22 | 22 | This is for fixing a few rotted sections of soffit - 1"x12"x6' common pine
Fascia - Straight | 2 | ea | 9.5 | 19 | This is for fixing a few rotted sections of soffit - s4s KD Pine 1x4x8
Trim Nails | 1 | box | 4 | 4 | 1-1/2 in. Stainless Finishing Nails (50-Pack)
Subtotal |  |  |  | 80
INSULATION (south facing updated siding)
Component / Description | Quantity | Unit | Unit Cost | Line Total | Notes
Batt Insulation R-15 | 6 | pack | 75 | 450 | R-15 Unfaced Fiberglass Insulation Batt 15 in. x 93 in.- 77 sq ft per bag
Subtotal |  |  |  | 450
GUTTERS
Component / Description | Quantity | Unit | Unit Cost | Line Total | Notes
Gutter Corner | 5 | ea | 16 | 80 | 5"x10'
Gutter Outlet | 4 | ea | 11 | 44
Gutter Connector | 7 | pack | 8.8 | 61.6 | Includes 2 per pack
Gutter Downspout Elbow | 4 | ea | 6 | 24 | 3"x4"x10"
Gutter Downspout | 4 | ea | 33 | 132 | 3"x4"x10"
Straight Gutter Section | 10 | ea | 18 | 180 | 5"x10'
Subtotal |  |  |  | 521.6
WINDOWS + PATIO DOOR
Component / Description | Quantity | Unit | Unit Cost | Line Total | Notes
Replacement Windows (double-hung) | 5 | ea | 200 | 1000 | South facing windows, 4x - 36x60, 1x - 36x36
Sliding Patio Door (6ft) | 1 | ea | 580 | 580 | 72x80 ply gem slider
Door Flashing
Foam Sealant (cans) | 2 | can | 10 | 20 | Low-expansion, around window/door frames
Window Flashing | 3 | roll | 20 | 60 | 6'x50' peel and stick
Window Mull | 1 | ea | 160 | 160 | Ply Gem Mull kit for 36x60 windows - price includes extra shipping
Exterior Caulk (tubes) | 4 | tube | 8 | 32 | 100% silicone, around trim perimeter
Subtotal |  |  |  | 1852
EXTERIOR PAINT (~1,050 sq ft)
Component / Description | Quantity | Unit | Unit Cost | Line Total | Notes
Exterior Paint | 6 | gal | 32 | 192 | Semi-gloss SW (Lowes)
Paint Brush | 1 | ea | 13 | 13 | For trim and cut-in
Paint Roller Covers | 1 | pack | 12 | 12 | X-Large nap for siding texture
Tape | 1 | pack | 20 | 20 | 6-rolls per pack
Subtotal |  |  |  | 237
FENCE (full perimeter, 5 pipe sections)
Component / Description | Quantity | Unit | Unit Cost | Line Total | Notes
Wood Post | 22 | ea | 12 | 264 | Added every 8', PT 4x4x8
Horizontal Rails | 22 | ea | 5.2 | 114.4 | 2 rails per 8' section
Post Concrete (50lb bags) | 44 | bag | 5.5 | 242 | ~2 bags per post, 60 lbs
Gate Hardware Kit | 1 | ea | 30 | 30 | Caps, bands, ties, rail ends
Screws | 1 | box | 33 | 33 | #8, 1 5/8, 5lb box
Pickets | 176 | ea | 4 | 704 | Vertical Pine PT, 5/8x5.5x6'
Subtotal |  |  |  | 1387.4
WALL FRAMING REPAIR (damaged studs)
Component / Description | Quantity | Unit | Unit Cost | Line Total | Notes
2×4 Studs (8ft) | 6 | ea | 3.5 | 21 | Stud replacement and sistering
Framing Nails (left over) | 1 | box | 0 | 0 | Construction screws for framing
Blocking / Misc Lumber | 1 | ea | 3.5 | 3.5 | Backing and blocking material
Subtotal |  |  |  | 24.5
ELECTRICAL (Rough-In Materials)
Component / Description | Quantity | Unit | Unit Cost | Line Total | Notes
Wire 12/2 (500 ft rolls) | 3 | roll | 200 | 600 | 500 ft 12/2 per roll
Wire 10/3 - Dryer + Water Heater | 1 | roll | 325 | 325 | 100 ft for both clothes dryer and water heater (each 50 ft)
Ceiling Fans | 3 | ea | 150 | 450 | Primary bedroom + 2 secondary bedrooms
Receptacles (10-ct box) | 6 | box | 26 | 156 | 10 receptacles per box
Wing-Nut Wire Connectors (250-ct) | 1 | box | 40 | 40 | 250-ct
Recessed Lights (left over) | 15 | ea | 0 | 0
Leviton Light Switches (10-ct pk) | 2 | box | 20 | 40 | 10 switches per box
Electrical Boxes - Double | 5 | ea | 4.6 | 23 | paddle work box
Electrical Boxes - Single Deep | 16 | ea | 4.15 | 66.4 | paddle work box
Electrical Boxes - Single Shallow | 44 | ea | 2.15 | 94.6 | paddle work box
Face Plates - Double | 10 | ea | 2 | 20 | Leviton decora
Face Plates - Single (10-ct pack) | 7 | pack | 7.7 | 53.9 | Single pack of 10 - Leviton decora
Smoke Detectors | 6 | ea | 20 | 120
Subtotal |  |  |  | 1988.9
HVAC
Component / Description | Quantity | Unit | Unit Cost | Line Total | Notes
Ducting | 1 | lot | 750 | 750 | Flex + rigid duct run
MR Cool 3-Ton Unit | 1 | ea | 4000 | 4000 | Condenser + lineset + air handler
HVAC Vent Covers | 5 | ea | 15 | 75 | Supply & return register covers
Subtotal |  |  |  | 4825
WATER HEATER
Component / Description | Quantity | Unit | Unit Cost | Line Total | Notes
Water Heater (40-gal electric) | 1 | ea | 500 | 500 | 40-gal tank unit
Wire 10/3 (50 ft) | 1 | roll | 0 | 0 | Price listed under electrical - 30 amp @ 50 ft - 10/3 for water heater circuit
Subtotal |  |  |  | 500
DOORS (6 Total)
Component / Description | Quantity | Unit | Unit Cost | Line Total | Notes
Doors (Interior slab) | 5 | ea | 72 | 360 | Door slab — casings are good
Door Handle Exterior | 2 | ea | 75 | 150
Door Handle Closets | 6 | ea | 15 | 90
Door Handle with Locks | 5 | ea | 20 | 100
Shims | 6 | pack | 1.78 | 10.68 | Wood shims
Flush Finish Screws | 1 | box | 10 | 10 | Door installation screws — 100 ct
Subtotal |  |  |  | 720.68
INTERIOR PAINT (walls, trim & doors)
Component / Description | Quantity | Unit | Unit Cost | Line Total | Notes
Interior Paint (Walls) | 20 | gal | 20 | 400 | BOGO 5-gal buckets, price per gal
Interior Paint (Doors/Trim) | 3 | gal | 53 | 159 | Semi-gloss SW (Lowes)
Paint Brushes | 2 | ea | 13 | 26 | Angled cut brushes + standard
Paint Roller Covers | 1 | pack | 12 | 12 | Small nap for interiors
Tape | 1 | pack | 20 | 20 | 6-rolls per pack
Caulking (silicone) | 14 | tube | 8 | 112 | 100% silicone, 24hr dry — trim gaps
Subtotal |  |  |  | 729
1/2 BATH RENOVATION
Component / Description | Quantity | Unit | Unit Cost | Line Total | Notes
Wall/Floor Tile | 25 | sq ft | 3 | 75 | 25 sq ft — verify sq ft needed
Pre-mixed Grout | 1 | ea | 20 | 20 | 1 qt pre mixed grout
Tile Thinset | 1 | gal | 36 | 36 | White Premixed Thin-Set
Tile Leveling Post | 1 | box | 13 | 13 | 100 post
Soffit Vent | 1 | ea | 18 | 18
Exhaust Duct Coupler | 1 | ea | 8 | 8
Exhaust Ducting | 1 | ea | 34 | 34 | 4"x25' each
Exhaust Fan | 1 | ea | 30 | 30 | 50 cfm
Tile Leveling Caps | 1 | box | 28 | 28 | 100 caps
Toilet | 1 | ea | 149 | 149
Bathroom Mirror | 1 | ea | 35 | 35
Faucet | 1 | ea | 50 | 50
Bathroom Light Fixture | 1 | ea | 45 | 45
Subtotal |  |  |  | 541
FULL BATH RENOVATION
Component / Description | Quantity | Unit | Unit Cost | Line Total | Notes
Curtain Rod | 1 | ea | 30 | 30
Faucet | 1 | ea | 120 | 120
Shower Valve and Fixture | 1 | ea | 200 | 200
Shower Curtain | 1 | ea | 30 | 30
Vanity Top | 1 | ea | 150 | 150 | Top + Sink, 49"
Vanity | 1 | ea | 400 | 400
Plumbing Rough In (Sink) | 1 | ea | 100 | 100 | Shifting the sink over 1 ft
Soffit Vent | 1 | ea | 18 | 18
Exhaust Duct Coupler | 1 | ea | 8 | 8
Exhaust Ducting | 2 | ea | 34 | 68 | 4"x25' each
Exhaust Fan | 1 | ea | 120 | 120 | 80 cfm
Bathroom Mirror | 1 | ea | 120 | 120 | 40" Mirror
Bathroom Light Fixture | 1 | ea | 50 | 50
Subtotal |  |  |  | 1414
LAUNDRY UPDATE (24'×8' wall)
Component / Description | Quantity | Unit | Unit Cost | Line Total | Notes
Dryer Exhaust Wall Box | 1 | box | 50 | 50
Drywall (1 sheet) | 1 | sheet | 15 | 15 | To hide ducting through garage closet
2×4 Lumber for Framing | 6 | ea | 4 | 24 | Wall framing to enclose utility area
Dryer Electrical | 1 | roll | 0 | 0 | 30 amp breaker @ 50 ft requiring 10/3 wire - cost listed under electrical section
Exhaust Ducting | 4 | ea | 15 | 60
Subtotal |  |  |  | 149
GARAGE CEILING DRYWALL (12'×18')
Component / Description | Quantity | Unit | Unit Cost | Line Total | Notes
Drywall (5/8 fire-x) | 20 | sheet | 20 | 400 | Ceiling panels
Drywall Screws (4,000 ct) | 1 | box | 50 | 50
Drywall Tape (250 ft) | 2 | roll | 4.5 | 9
Drywall Mud (3.5 lb boxes) | 4 | box | 13 | 52
Subtotal |  |  |  | 511
COVERED DECK (19'×16' = 304 sq ft)
Component / Description | Quantity | Unit | Unit Cost | Line Total | Notes
Metal Roof Panels | 18 | panel | 28 | 504 | 12'×2' panels (mix 12' and 8' to save)
Deck Boards 14' | 5 | ea | 11.5 | 57.5 | 5/4×4×14' — repairing damaged boards
Deck Boards 16' | 4 | ea | 13 | 52 | 5/4×4×16' — repairing damaged boards
Deck Paint | 2 | gal | 45 | 90
Subtotal |  |  |  | 703.5
SHED REMOVAL
Component / Description | Quantity | Unit | Unit Cost | Line Total | Notes
Dumpster / Haul Fee | 1 | lot | 150 | 150 | Confirm dump truck availability and timing
Subtotal |  |  |  | 150