## Vendor History
Vendor/Contractor History Log (Per Job / Work Instance)
Date | Company Name | Project / Job | Trade | Quality (1–5) | Schedule (1–5) | Communication (1–5) | Cost (1–5) | Weighted Total | Notes / Context | Evaluator
2026-03-07 | Company 1 | Full Renovation Management | General Contractor | 5 | 4 | 5 | 5 | 4.7 |  | JR
2026-03-08 | Company 2 | Foundation Pier Install | Foundation Contractor | 4 | 3 | 3 | 4 | 3.5 |  | JR
2026-03-09 | Company 3 | Garage Demolition | General Contractor | 3.5 | 4 | 3 | 4 | 3.6 |  | JR
2026-03-10 | Company 3 | Attic Insulation | General Contractor | 3.5 | 4 | 4 | 3 | 3.7 |  | JR
2026-03-11 | Company 4 | Roof Replacement | Roofing Contractor | 2 | 1 | 2 | 3 | 1.8 |  | JR
2026-03-12 | Company 3 | Kitchen Structural Beam | General Contractor | 3.5 | 5 | 3 | 3.5 | 3.85 |  | JR
2026-03-13 | Company 2 | Driveway Replacement | Foundation Contractor | 3 | 4 | 4 | 3 | 3.5 |  | JR
2026-03-14 | Company 4 | Roof Repair | Roofing Contractor | 2 | 1 | 3 | 2 | 1.9 |  | JR
2026-03-15 | Company 1 | New House Build Project Management | General Contractor | 5 | 5 | 5 | 5 | 5 |  | JR
2026-03-16 | Company 2 | Sidewalk Replacement | Foundation Contractor | 2 | 4 | 4 | 2 | 3 |  | JR
2026-03-17 | Company 2 | Concrete Patio Replacement | Foundation Contractor | 4 | 4 | 3.5 | 3 | 3.8 |  | JR
2026-03-18 | Company 2 | Garage Pier Install | Foundation Contractor | 3 | 3 | 4 | 4 | 3.3 |  | JR

## History Summary
History Summary — Auto-Calculated from Vendor/Contractor History
Company Name | Trade | Total Jobs | Overall Avg | Last Date | Last Score | Avg (Last 90d) | Avg (Prior 90d) | Trend | Recommendation
Company 1 | General Contractor | 2 | 4.85 | 2026-03-15 | 5 | 4.85 | - | N/A | Preferred
Company 2 | Foundation Contractor | 5 | 3.42 | 2026-03-18 | 3.3 | 3.42 | - | N/A | Acceptable
Company 3 | General Contractor | 3 | 3.7167 | 2026-03-12 | 3.85 | 3.7167 | - | N/A | Acceptable
Company 4 | Roofing Contractor | 2 | 1.85 | 2026-03-14 | 1.9 | 1.85 | - | N/A | Caution
Score Guide: | ≥ 4.0 = Preferred |  | 3.0–3.9 = Acceptable |  | < 3.0 = Caution
Notes: | Trend compares Avg (Last 90d) vs Avg (Prior 90d). Requires entries on both sides of the 90-day window to calculate.
Formulas:
Last Date = IFERROR(SINGLE(MAXIFS('Vendor History'!A$3:A1000,'Vendor History'!B$3:B1000,[Company Name])),"-")
Last Date = IFERROR(MAXIFS('Vendor History'!A$3:A1000,'Vendor History'!B$3:B1000,[Company Name]),"-")
Avg (Last 90d) = IFERROR(AVERAGEIFS('Vendor History'!I$3:I1000,'Vendor History'!B$3:B1000,[Company Name],'Vendor History'!A$3:A1000,">="&(TODAY()-90)),"-")
Avg (Prior 90d) = IFERROR(AVERAGEIFS('Vendor History'!I$3:I1000,'Vendor History'!B$3:B1000,[Company Name],'Vendor History'!A$3:A1000,"<"&(TODAY()-90)),"-")

## How This Works
Rauck Built LLC — Vendor & Contractor Scorecard
How This Workbook Works — Field Reference Guide
0
Purpose of This Workbook
0
This workbook captures and summarizes contractor performance across jobs. The Vendor History sheet logs individual job scores. The History Summary sheet automatically aggregates those scores into unbiased, comparable trends — so every hiring decision is backed by actual field data.
How the Vendor History Log Works
| ▸ | Each row represents one completed job or meaningful work instance.
| ▸ | Scores should reflect actual performance given known constraints at the time of work.
| ▸ | Weather, access issues, and client-caused delays should already be factored into the score — not used to override it after the fact.
Rating Scale (1–5 for all categories)
| Score | Meaning
| 5 | Excellent — Exceeded expectations on this job
| 4 | Good — Met expectations on this job
| 3 | Acceptable — Minor issues, still workable
| 2 | Poor — Recurring issues, caused problems
| 1 | Unacceptable — Failed to deliver on expectations
Scoring Category Weights
| Category | Weight | Why It Matters
| Category | Weight | Why It Matters
| Quality | 40% | Workmanship is the primary deliverable — defects cost real money to fix
| • | Work is installed correctly per scope, code, and industry standard
| • | Surfaces, framing, and finishes are plumb, level, square, and clean
| • | Minimal callbacks, punch list items, or rework required after completion
| • | Work passes inspection on the first attempt
| Schedule | 30% | Project timelines affect carrying costs and downstream trades
| • | Job is completed within the quoted timeframe or with justified explanation
| • | Delays are communicated proactively — not discovered after the fact
| • | Work does not stall other trades or create downstream scheduling problems
| Communication | 20% | Responsiveness and transparency reduce surprises on job sites
| • | Responds to calls and texts within a reasonable timeframe during active jobs
| • | Flags problems, delays, or scope issues early — before they compound
| • | Change orders and substitutions are communicated clearly and in writing
| • | Shows up when they say they will, or gives advance notice when they cannot
| Cost | 10% | Bids are evaluated upfront; cost score reflects adherence to agreed scope
| • | Final invoice matches the agreed bid or contract amount
| • | Change orders are documented, reasonable, and approved before work proceeds
| • | No surprise line items or scope creep billed without prior discussion
Weighted Total = (Quality × 0.40) + (Schedule × 0.30) + (Communication × 0.20) + (Cost × 0.10)
Decision Philosophy
▸ Scores reflect context, not excuses.
Scores are entered with known constraints already considered. Do not go back and modify historical scores to account for context — that defeats the purpose of an objective baseline.
▸ The History Summary is the unbiased baseline.
Use the Summary sheet to compare vendors across jobs. It removes recency bias and one-off impressions from the decision.
▸ Administrative decisions live in your CRM.
Approval status, probation, and do-not-use flags belong in Microsoft Lists — not in this workbook. Keep scoring and administration separate.
Rauck Built LLC · Vendor & Contractor Scorecard · Internal Use Only